## School Initiatives - Priority
|  |  |  | 70 | 70 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 0 | 0
| Project Management |  |  | Meeting Scheduling and Time Allocation (80 Minutes / Meeting)
Project ¦ Action Item | Responsible | Status | Link | 2022-03-31 | 2022-04-30 | 2022-05-30 | 2022-06-29 | 2022-07-29 | 2022-08-28 | 2022-09-27 | 2022-10-27 | 2022-11-26 | 2022-12-26 | 2023-01-25 | 2023-02-24 | 2023-03-26
Implement Schools Committee Improvement Plan | Staub, Lon | In Process | Improvement Plan
[1] Provide update on Exec Comm infrastructure project | Marcus, Annette | In Process
[2] Review and approve strategic planning process and high-priority initiatives | Staub, Lon | Achieved |  | 2022-03-31: 15; 2023-01-25: 45
[3] Draft and review school suicide-prevention "ecosystem" (see below) | Delbridge, Spencer | In Process
[4] Review and approve agenda-planning process / calendar for recurring tasks | Staub, Lon | In Process |  | 2022-03-31: 20
[5] Discuss / update member expectations | Staub, Lon | Achieved |  | 2022-12-26: 45
[6] Evaluate member resources and requirements / develop recruitment plan | Staub, Lon | In Process |  | 2022-03-31: 35; 2022-04-30: 30
[7] Provide update on youth-participation guidance | Marcus, Annette | In Process
[8] Provide DEI guidance | Marcus, Annette | In Process
YSIPP Initiatives
Monitor and Provide Guidance for Adi's Act, including Infrastructure Evaluation | Staub, Lon | Planning
Draft, review and approve Adi's Act project plan | Staub, Lon | Planning |  | 2022-05-30: 45
Share / approve school suicide-prevention "ecosystem" | Delbridge, Spencer | In-Process |  | 2022-05-30: 45
Problem-solve low usage by schools of training resources [Kimberlee, Angi] | TBD | Planning
Monitor Other YSIPP Initiatives w/ Impact to Schools | Staub, Lon | Planning
OHA to lead exploration on K2 suicide-prevention programming | Hochstetler, S | In Action
OHA-funded school-based providers to receive training recommendations and tracking tools | Pearson, Fran | Achieved
ODE to proceed with rulemaking for SB 52 (2021) to outline LGBTQ2SIA+ policies | Foster-Lawson, Angie | In Action
Other Informational Updates and Proposed Projects
Info Update: School Safety Task Force | Marcus, Annette
Conference Presentation(s): School Superintendents / Psychologists / Counselors? | Marcus, Annette
Agency Updates: OHA / ODE / Lines for Life | Potts, Justin |  |  | 2022-04-30: 20
Legislative Planning and Update
Research Update: U of O |  |  |  | 2022-04-30: 20
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 70 | 70 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 0 | 0
Note on A6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: for clarification on committee roles / responsibilities
Note on A12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Evaluate SoS training as source for youth involvement [Justin Potts]
Note on A19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Root causes include inadequate funding, staff availability, and lack of community engagement.
Note on A30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Trends, what's going on in-state, resources available, unique approaches, educational opportunities.

## YSIPP Initiatives - Extract
YSIPP 2.0 Initiatives w/ Education System Impact |  |  |  |  | Ownership |  | Priority |  |  | Project Management |  |  | Notes
Pillar | Goal | Pathway | Filter | Initiative | Responsibile Unit Organization Type ¦ Org Name ¦ Etc. | Responsible Person | Ease | Impact | Resources Required (Hours) | Due Date | Progress Status | Project ID and Link | Questions / Requests | Other
N/A | N/A | N/A |  | Schools Committee Improvement Plan | Pub Health ¦ Alliance ¦ Comm ¦ Schools | Staub, Lon |  | High |  |  | In Action
1 - Healthy & Empowered Families | 1.1. - Integrated and Coordinated Activities | 1.1.1. - Coordinated Activities | Big River - Other | Big River statewide coordinators meet monthly to align work, give program updates, connect and learn. | Pub Health ¦ OHA ¦ Coordinator | Hochstetler, Shanda |  |  |  |  | Achieved
1 - Healthy & Empowered Families | 1.1. - Integrated and Coordinated Activities | 1.1.1. - Coordinated Activities | Big River - Other | Big River statewide coordinators are equipped to bridge interested organizations and people to related suicide prevention work including other Big River programs and statewide suicide prevention efforts. | Pub Health ¦ OHA ¦ Coordinator | Hochstetler, Shanda |  |  |  |  | In Action
1 - Healthy & Empowered Families | 1.1. - Integrated and Coordinated Activities | 1.1.1. - Coordinated Activities | Adi's Act | Fall coordination meetings between contracted coordinators and specialists supporting Adi's Act implementation, Oregon Department of Education (ODE), and OHA coordinators are scheduled with each Educational Service District. | Pub Health ¦ OHA ¦ Coordinator | Hochstetler, Shanda |  |  |  |  | Planning
1 - Healthy & Empowered Families | 1.2 - Media and Communications | 1.2.2. - Promoting Wellness | Big River - SoS | Sources of Strength will continue to promote positive culture change in Oregon schools K-12 and post-secondary and will continue to grow program reach to other youth-serving spaces. | Pub Health ¦ OHA ¦ Coordinator | Hochstetler, Shanda |  |  |  |  | Achieved |  | Utilize SoS course offerings as means for youth recruitment? (J. Potts)
1 - Healthy & Empowered Families | 1.4 - Coping and Connection | 1.4.1 - Positive Connections | Big River - SoS | Sources of Strength programming available statewide for all students Grade 3 to postsecondary. | Pub Health ¦ OHA ¦ Coordinator | Hochstetler, Shanda |  |  |  |  | Achieved
1 - Healthy & Empowered Families | 1.4 - Coping and Connection | 1.4.2 - Coping Strategies | Big River - SoS | Sources of Strength Elementary (grades 3-5) suicide prevention programming is available statewide. | Pub Health ¦ OHA ¦ Coordinator | Hochstetler, Shanda |  |  |  |  | Achieved
1 - Healthy & Empowered Families | 1.4 - Coping and Connection | 1.4.2 - Coping Strategies |  | New: Explore possibilities for K-2 suicide prevention programming | Pub Health ¦ OHA ¦ Coordinator | Hochstetler, Shanda |  |  |  |  | In Action |  | Darcy w/ Matchstick facilitates training, garner support. YouthSave being adapted to address elementary students. (Shanda)
1 - Healthy & Empowered Families | 1.4 - Coping and Connection | 1.4.3 - Adult Roles | Big River - SoS | Sources of Strength makes Adult Advisor training available widely for youth-connected adults in areas with Sources programming. | Pub Health ¦ OHA ¦ Coordinator | Hochstetler, Shanda |  |  |  |  | In Action |  | Issue: Schools not signing on. Why or why not? Help schools address resources. (Kimberlee). Time / funding an issue, especially for elementary. (Angie). Community-driven, when effective (Kimberlee).
2 - Clinical & Community Services | 2.1 - Frontline and Gatekeeper Training | 2.1.1. - Appropriately Trained Adults |  | The K-12 school sector based resource called the "Suicide Prevention, Intervention, Postvention: Step By Step" will be available at no cost. This resource outlines recommendations for appropriate level of training and retraining recommendations. | Pub Health ¦ OHA ¦ Coordinator | Hochstetler, Shanda |  |  |  |  | Achieved |  | Oregon-specific, updated annually (Shanda)
2 - Clinical & Community Services | 2.1 - Frontline and Gatekeeper Training | 2.1.1. - Appropriately Trained Adults |  | New: All OHA-funded school based mental health providers will receive recommendations and tracking tools for retraining for appropriate level of suicide prevention, intervention and postvention training. | Pub Health ¦ OHA ¦ Child and Family Behavioral Health | Pearson, Fran |  |  |  |  | Achieved |  | Required to receive SP training (Shanda)
2 - Clinical & Community Services | 2.1 - Frontline and Gatekeeper Training | 2.1.2 - Supported Training Options | Big River - Other | OHA will support Big River Programming by providing low or no cost access to Train-the-Trainer events, statewide coordination, evaluation support, and limited course support for the following programs: | Pub Health ¦ OHA ¦ Coordinator | Hochstetler, Shanda |  |  |  |  | Achieved
2 - Clinical & Community Services | 2.1 - Frontline and Gatekeeper Training | 2.1.2 - Supported Training Options | Big River - Other | Basic suicide prevention training options are available statewide and include Question, Persuade, Refer (QPR), Youth Mental Health First Aid, and Adult Mental Health First Aid. | Pub Health ¦ OHA ¦ Coordinator | Hochstetler, Shanda |  |  |  |  | Achieved
2 - Clinical & Community Services | 2.1 - Frontline and Gatekeeper Training | 2.1.2 - Supported Training Options | Big River - Other | Enhanced suicide prevention training options are available statewide for mental health providers including Youth Suicide Assessment in Virtual Environments (YouthSAVE), Collaborative Assessment and Management of Suicidality (CAMS), Cognitive Behavioral Therapy - Suicide Prevention (CBT-SP), and Assessing and Managing Suicide Risk (AMSR). | Pub Health ¦ OHA ¦ Coordinator | Hochstetler, Shanda |  |  |  |  | Achieved
2 - Clinical & Community Services | 2.1 - Frontline and Gatekeeper Training | 2.1.3 - Representative Trainers | Big River - Other | Big River statewide coordinators will continue to assess the gaps in availability of culturally and linguistically diverse trainers and trainings and will recruit accordingly and in collaboration with other Big River statewide coordinators. | Pub Health ¦ OHA ¦ Coordinator | Hochstetler, Shanda |  |  |  |  | Early Action
2 - Clinical & Community Services | 2.3 - Protective Programming | 2.3.3 - Protective Policies | Adi's Act | Adi's Act plans are legislatively mandated for each school district in Oregon. District plans are due in Oct 2021 to ODE. | Education ¦ ODE ¦ Comm Heath and Wellness | Boulahanis, Kara |  |  |  |  | In Action
2 - Clinical & Community Services | 2.3 - Protective Programming | 2.3.3 - Protective Policies | Adi's Act | School Suicide Prevention and Wellness Specialists (also called the Adi's Act support team) provides support to school districts for writing, implementing, and updating Adi's Act plans (5.0 FTE) | Pub Health ¦ OHA ¦ Coordinator | Hochstetler, Shanda |  |  |  |  | Achieved
2 - Clinical & Community Services | 2.3 - Protective Programming | 2.3.3 - Protective Policies | Adi's Act | School Safety and Prevention Specialists (11.0 FTE) are housed in Educational Service Districts (ESD) and funded by ODE to support ESD's regarding Sect 36 of the Student Success Act, which includes suicide prevention. | Education ¦ ODE ¦ School Safety Coordinator | Delbridge, Spencer |  |  |  |  | Achieved
2 - Clinical & Community Services | 2.3 - Protective Programming | 2.3.3 - Protective Policies | Adi's Act | New: Annual coordination meetings (starting September 2021) to align communication and coordination for Adi's Act implementation between ESD's, LFL, OHA and ODE. | Pub Health ¦ OHA ¦ Coordinator | Hochstetler, Shanda |  |  |  |  | Planning
2 - Clinical & Community Services | 2.3 - Protective Programming | 2.3.3 - Protective Policies |  | New: ODE will proceed with rulemaking for SB 52 (2021) to outline protective policies for the LGBTQ2SIA+ population. | Education ¦ ODE ¦ Student Success Coordinator | Foster-Lawson, Angie |  |  |  |  | In Action |  | Angie started Monday.
2 - Clinical & Community Services | 2.3 - Protective Programming | 2.3.3 - Protective Policies | Adi's Act | New: University of Oregon Suicide Prevention Lab will lead a pilot project for evaluating and monitoring implementation of Adi's Act plan. Advised by ODE, OHA, and representation from Big River coordinators. | Partners ¦ U of O ¦ Suicide Prevention Lab | Seeley, John |  | High |  |  | Early Action
2 - Clinical & Community Services | 2.3 - Protective Programming | 2.3.3 - Protective Policies | Adi's Act | New: Monitor implementation of plans for Adi's Act, increase meaningful participation in Adi's Act from school districts, and increase the use of best practices in school districts. Organize infrastructure and clarify roles and responsibilities. | Pub Health ¦ Alliance ¦ Comm ¦ Schools | Staub, Lon |  | High |  |  | Early Action |  | Implementation must address culture, relationship-building (Shanda). Policies may not be in place in some schools. Need exemplar plans that can be shared. (Angi) Emphasize successful plans. Address diversity, cultural sensitivity in plans. (Mila). Engaging the community in support, implementation (Kimberlee).
3 - Treatment & Support Services | 3.3 - Appropriate Treatment of Suicidality | 3.3.1 - Equipped Workforce | Big River - Other | Enhanced training options in Big River programming menu available statewide - Youth SAVE, Collaborative Assessment and Management of Suicidality (CAMS), Assessing and Managing Suicide Risk (AMSR) | Pub Health ¦ OHA ¦ Coordinator | Hochstetler, Shanda |  |  |  |  | Achieved |  | Substantively identical to Row 21?
3 - Treatment & Support Services | 3.3 - Appropriate Treatment of Suicidality | 3.3.1 - Equipped Workforce | Big River - Other | Advanced training options in Big River programming menu available statewide - Cognitive Behavioral Therapy - Suicide Prevention (CBT-SP), Dialectical Behavioral Therapy - Skills and Suicide Prevention modules (DBT) | Pub Health ¦ OHA ¦ Coordinator | Hochstetler, Shanda |  |  |  |  | Achieved |  | Substantively identical to Row 21?
End Input Range
0 - All
1 - Healthy & Empowered Families
2 - Clinical & Community Services
3 - Treatment & Support Services
0 - All
1.1. - Integrated and Coordinated Activities
1.2 - Media and Communications
1.4 - Coping and Connection
2.1 - Frontline and Gatekeeper Training
2.3 - Protective Programming
3.3 - Appropriate Treatment of Suicidality
0 - All
1.1.1. - Coordinated Activities
1.2.2. - Promoting Wellness
1.4.1 - Positive Connections
1.4.2 - Coping Strategies
1.4.3 - Adult Roles
2.1.1. - Appropriately Trained Adults
2.1.2 - Supported Training Options
2.1.3 - Representative Trainers
2.3.3 - Protective Policies
3.3.1 - Equipped Workforce
High
[5 empty] | Pub Health |  |  | Med
[5 empty] | Pub Health ¦ OHA |  |  | Low
Pub Health ¦ OHA ¦ Director
Pub Health ¦ OHA ¦ Coordinator
Pub Health ¦ OHA ¦ Child and Family Behavioral Health
Pub Health ¦ County
Pub Health ¦ Alliance
Pub Health ¦ Alliance ¦ Staff
Pub Health ¦ Alliance ¦ Members
Pub Health ¦ Alliance ¦ Comm
Pub Health ¦ Alliance ¦ Comm ¦ Exec
Pub Health ¦ Alliance ¦ Comm ¦ Data & Eval
Pub Health ¦ Alliance ¦ Comm ¦ Outreach
Pub Health ¦ Alliance ¦ Comm ¦ Schools
Pub Health ¦ Alliance ¦ Comm ¦ Transitions of Care
Pub Health ¦ Alliance ¦ Comm ¦ Workforce
Pub Health ¦ Alliance ¦ Advisory ¦ Faith
Pub Health ¦ Alliance ¦ Advisory ¦ LGBTQ
Pub Health ¦ Alliance ¦ Advisory ¦ Lived Experience
Pub Health ¦ Alliance ¦ Advisory ¦ Youth
Education ¦ ODE
Education ¦ ODE ¦ Comm Heath and Wellness
Education ¦ ODE ¦ School Safety Coordinator
Education ¦ ODE ¦ Student Success Coordinator
Education ¦ ESD
Education ¦ ESD ¦ School Safety & Prevention Specialists
Education ¦ School Districts
Education ¦ Schools
Education ¦ Schools ¦ Principal
Education ¦ Schools ¦ Teacher
Education ¦ Schools ¦ Teacher
Partners ¦ AOCMHP
Partners ¦ U of O
Partners ¦ U of O ¦ Suicide Prevention Lab
Partners ¦ Lines for Life
Partners ¦ Lines for Life ¦ SSPW Manager
Partners ¦ Lines for Life ¦ SSPW Coordinator
Partners ¦ Matchstick
Partners ¦ Oregon Pediatric
Baker, Jill
Delbridge, Spencer
Fraga, Jenn
Hochstetler, Shanda
Marcus, Annette
Rochelle, John
Seeley, John
Staub, Lon
TBD
1
2
3
4
5
How
When
Who