## Sheet1
Timeline
Initiative / Action Item | Committee Role Responsible Accountable Support Consult Inform Monitor ADvocate | Implementation of Committee Role | Status, as it relates to TOC Role | May 2022 | June 2022 | July 2022 | August 2022 | September 2022 | October 2022 | November 2022 | December 2022 | January 2023 | February 2023 | March 2023 | April 2023 | May 2023 | June 2023 | July 2023
HB 3090 Report Recommendations | AD - TOC Committee | Receive draft report and provide recommendations. When report is finalized, create a monitoring plan for how the committee would like to stay engaged with this work moving forward. | Achieved | TOC draft letter by May 27 for Exec | Send letter to OHA about date for report |  | Received final report from OHA | Review final report Finalize monitoring plan Send to OHA
To address the Lack of Understanding about how policies are meeting intended goals, The Legislature should integrate these requirements into larger behavioral health improvement efforts, such as the Behavioral Health Committee required by HB 2086 (2021), to support robust accountability metrics. This outcome and performance management should consider the unique barriers of and for the following: » Hospitals in different regions of the state » Populations, including children » Houseless adults, and » Patients who experience substance use disorders (SUD) with co-occurring disorders. | C / M - TOC Committee | TOC request that someone from the TOC is able to be part of this Behavioral Health Committee. The BH Committee mentioned is under the Oregon Health Policy Board. | In Progress |  |  |  |  | Committee to discuss who could be a representative on this BH Committee | Julie Magers contact Carol Dicky and will look into application process and apply, keeping TOC updated |  |  | Julie to provide any updates to TOC Committee on status
To address the Lack of Understanding on How Companion Bill, HB 3091, OHA will issue guidance for hospitals on how to receive reimbursement for required services. OHA will also recommend administrative rule changes needed to address reimbursement challenges. | M / AD - TOC Committee | TOC request updates from OHA in 6-month intervals from publication of final 3090 report and advocate when needed and appropriate. | Early Action | [9 empty] | TOC request status update from OHA on progress of this recommendation - has it happened, any progress, any barriers, etc.
To address the Lack of approved staff to provide services, OHA will propose changes to OARs to set criteria for what types of personnel can be trained to provide caring contacts. | M / AD- TOC Committee | TOC find contact at Lines for Life as they are a large contractor for providing caring contacts and learn what other organizations are contractors for this. See if they would be able to be an ongoing or ad-hoc TOC Committee member. TOC request updates from OHA in 6-month intervals from publication of final 3090 report and advocate when needed and appropriate. | Early Action | [8 empty] | Find potential contact at Lines for Life. Ask OHA for list of other large contractors for this work. | TOC request status update from OHA on progress of this recommendation - has it happened, any progress, any barriers, etc.
To address the Lack of approved staff to provide services, Hospitals should provide training to nurses and nurse case managers on: » Use of a person’s pronoun » Use of person-centered language, and » Techniques to identify psychosocial issues in a nonjudgmental way. | M / AD- TOC Committee | TOC request updates from OHA or OAHHS in 6-month intervals from publication of final 3090 report and advocate when needed and appropriate. | Early Action | [9 empty] | TOC request status update from OHA on progress of this recommendation - has it happened, any progress, any barriers, etc.
To address the Lack of approved staff to provide services, Hospitals should provide sufficient mental health training for staff, especially in rural areas. This training needs to be culturally responsive and trauma-informed. | M - TOC Committee | TOC request updates from OHA or OAHHS in 6-month intervals from publication of final 3090 report and advocate when needed and appropriate. | Early Action | [9 empty] | TOC request status update from OHA on progress of this recommendation - has it happened, any progress, any barriers, etc.