## All Alliance YSIPP Initiatives
Alliance YSIPP Initiative Tracker
STATUS | DEADLINE | DATE LAST UPDATED | YSIPP INITIATIVE NUMBER | INITIATIVE / TASK | COMMITTEE / ADVISORY | RASCI-AD | INITIATIVE DESIRED OUTCOME | TASK DELIVERABLE | NOTES / PROGRESS
In Progress | Adjust annually as needed | 2023-03-31 | 1.1.1.7 | INITIATIVE: The Oregon Alliance to Prevent Suicide (The Alliance) will organize committees, advisory groups, and workgroups to align with YSIPP 2021-2025. | Executive | Annette - A | Structure that aligns with Alliance assigned initiatives. |  | December: A request was sent to the Lethal Means Advisory to change group status to become a standing Alliance Committee. This will be discussed by the group next Quarter. Previously achieved tasks were removed. September: Structure confirmed last fiscal year. Currently exploring changing lethal means advisory to a committee. Invite co-chairs to attend exec in October.
Achieved | 2022-10-03 | 2023-03-31 |  | Review draft infrastructure documents listed above with Executive Committee for feedback and approval. | Staff | Annette - A Jenn - R Executive - C |  | Final materials available to be shared with full Alliance and processes will be finalized for Alliance infrastructure. | March: Documents voted on and approved by Executive. Now need to decide where they will live - by-laws, operations manual, website? December: Documents were reviewed but not voted on. Will ask for a vote next quarter to finalize this. August: Documents will be reviewed during October Executive Committee meeting.
In Progress | 2023-10-31 | 2023-02-28 |  | In the fall, assess whether any new committees or advisory groups are needed. (Fall timeline per Operations Manual CW1, page 15). | Staff | Annette - A Jenn - R Executive - C |  | Committee structure will stay relevant to YSIPP initiatives.
Not Started | 2023-07-31 | 2023-01-31 |  | Staff will review the Operations Manual and By-Laws annually and make any updates as needed. Potential updates to reflect changes made to Alliance processes including, but not limited to, voting process, new group workflow. | Staff | Annette - A |  | Alliance operations manual will be current and accurately reflect processes.
In Progress | Ongoing | 2023-03-31 | 1.1.1.11 | INITIATIVE: The Oregon Alliance to Prevent Suicide (Alliance) will identify and engage with key partners for equity work. | Equity Advisory | Annette - A | The Alliance will be able to meaningfully engage in equity work and engage with a wider group of community members in suicide prevention work.
In Progress | Ongoing | 2023-02-28 |  | Deepen and leverage existing relationships with DHS, NARA, and NAMI which each serve very high risk populations. |  |  |  |  | February: Presented Connect to NARA for cultural adaptation and recruited NARA Rep to assist with quarterly meeting on Boys and Men which will take place March 10th. Highlighting opportunities to collaborate with DHS on suicide prevention at Quarterly Webinar. Collaborating with NAMI on 988 advocacy.
Not Started | 2023-07-31 | 2023-02-28 |  | Identify 1-2 BIPOC organizations or communities to begin building relationship with.
Early Action | 2023-03-31 | 2023-03-31 | 1.1.3.2 | INITIATIVE: OHA and The Alliance will create a list of priority youth-serving community-based organizations with which to develop or maintain pathways for meaningful engagement. | Staff | Jenn - A | The Alliance will have a pathway to meaningfully engage with youth and young adults.
Achieved | 2023-01-31 | 2023-01-31 |  | Alliance leadership will meet with OHA about the Youth Era position and YYEA. | Staff | Jenn - A |  | Leadership will have an update to any progress or barriers OHA has with finding staffing Youth Era to run YYEA and have as a connection to the Alliance. | January: Galli, Annette, and Jenn met with Nikobi and others at OHA to discuss contract and staffing issues. OHA said they are working on the contract piece and finding a way to work around staffing issues. No next steps or dates were given. From the Alliance's view, we are waiting on OHA to figure this piece out.
In Progress | Ongoing | 2023-03-31 |  | Jenn will meet with staff at Healthy Transitions, Sources of Strength, YouthLine, NAFY, and Fourth Dimension to talk about how the Alliance can partner with them in their work. | Staff | Jenn - A |  | Staff will have a better understanding of how other organizations engage youth and begin connections to the Alliance. | March: Jenn met with Healthy Transitions and YouthLine to talk about partnership and around holding focus groups. Both were interested in partnering with the Alliance initially but follow-up and next steps have been difficult to accomplish. Jenn is working to connect with these groups to be able to hold at least one focus group before the end of the fiscal year. A meeting with Sources of Strength needed to be canceled and Jenn is waiting on a new meeting date. Executive approved the Alliance moving forward with partnering with NAFY for youth engagement. It was decided to use the youth engagement funding for a one-year pilot program instead of splitting the funds between two years. More information will come next quarter. February: Galli scheduled a meeting for Staff to meet with NAFY. Goal of meeting is to see how the Alliance and NAFY may be able to partner around youth engagement. Jenn will meet with Healthy Transitions, Sources of Strength, and YouthLine early to mid March to discuss partnership possibilities and potential focus groups. January: Jenn emailed staff at these organizations to set-up times to meet.
Achieved | 2023-03-31 | 2023-02-28 |  | Jenn will discuss the possibility of holding a focus group on the Lived Experience Survey with above listed partners. | Staff | Jenn - A |  | Potential partnership to collect current information on trends and other pieces of the lived experience survey that was distributed 2021. | March: Jenn met with Healthy Transitions and YouthLine to talk about partnership and around holding focus groups. Both were interested in partnering with the Alliance initially but follow-up and next steps have been difficult to accomplish. Jenn is working to connect with these groups to be able to hold at least one focus group before the end of the fiscal year.
In Progress | Ongoing | 2023-01-31 | 1.1.4.1 | INITIATIVE: Stipends are provided for youth representatives and people with lived experience that are not paid to attend state advisory committees. | Staff | Jenn - A | Youth, young adults, and others with lived experience that are not already compensated for participating with the Alliance will receive compensation.
Achieved | 2023-02-28 | 2023-01-31 |  | Jenn will reconnect with those who receive stipends from OHA after coming back from maternity leave. She will send out the annual self-attestation forms for completion and catch people up on any stipends they need submitted. | Staff | Jenn - A OHA - S |  | Stipends will be submitted on a regular basis to OHA for members.
In Progress | Ongoing | 2023-01-31 |  | Jenn will complete member stipend forms on a monthly basis (filling them out with meetings they attended and homework completed and send to the member for approval) and send them to OHA for processing. | Staff | Jenn - A Alliance Member & OHA - S |  | Stipends will be submitted on a regular basis to OHA for members.
Achieved | 2023-02-20 | 2023-02-28 |  | Jenn will ask Shanda to connect her with the new OHA person over stipends. | Staff | Jenn - A Shanda - S |  | Jenn will be aware of the new process for submitting stipends.
In Progress | Ongoing | 2023-03-31 | 1.1.4.2 | INITIATIVE: Youth representatives (including at least one person that has not yet reached age 18) serve on The Alliance. | Staff | Annette - A | The Alliance will have meaningful youth engagement.
Achieved | Ongoing | 2023-01-31 |  | The Alliance has one person under 18 on the Alliance and is actively engaged in advisory groups and committees. | Staff | Annette - A Jenn - R |  | Meaningful youth engagement.
In Progress | Ongoing | 2023-03-31 |  | Staff will work with youth organizations to recruit additional youth for the Alliance. | Staff | Jenn - A |  | Meaningful youth engagement. | March: The Alliance has received multiple young adult applications for Alliance membership, some of which are 17 and younger. Jenn will reach out to these folks to connect and learn more about their interests. February: Alliance Chair to ask Executive Committee to identify how they are going to support bringing more youth to Alliance work.
In Progress | Ongoing | 2023-01-31 |  | Staff will connect with existing youth and young adult members at least once a month. Staff will provide support around meeting engagement. | Staff | Jenn - A |  | Meaningful youth engagement.
In Progress | Ongoing | 2023-01-31 | 1.1.4.3 | INITIATIVE: The Alliance will develop a clear process to involve diverse youth input on key decisions with a variety of engagement strategies. | Staff | Jenn - A | The Alliance will have meaningful youth engagement.
Achieved | 2023-02-28 | 2023-01-31 |  | A clear process was approved by the Executive Committee in 2022 which includes holding focus groups for youth on different topics throughout the year as needed and as committees ask. | Staff | Jenn - A OHA - S |  | Better understanding of the ask behind the YSIPP Initiative. | February: Town Hall Process that was approved by Executive Committee. Every year for Capitol Day, have a focus on bringing youth to the event.
In Progress | 2023-06-30 | 2023-02-28 |  | During legislative session, focus will be on supporting youth and young adults to engage in legislative advocacy. | Staff | Annette / Jenn - A |  | Youth engagement in legislative process as able. | February: 18-year-old Alliance member engaged in Capitol Days.
In Progress | 2023-12-31 | 2023-03-31 | 1.1.5.5 | INITIATIVE: The Alliance will develop an equity screening tool for suicide prevention and train Alliance committees and suicide prevention coalitions on the tool. | Equity Advisory | Annette - A | The Alliance will have a consistent way to measure Alliance initiatives and with an equity lens.
In Progress | Ongoing | 2023-01-31 |  | Annette will present the equity tool to the coalitions as they are ready to hear about the tool. | Staff | Annette - A |  | One coalition will be trained on the tool and Staff will receive feedback from a coalition on how it can be implemented and any questions. | January: Annette presented the tool during Clackamas County's coalition in January. This was recorded for members to watch at a future date as well.
In Progress | 2023-06-30 | 2023-03-31 |  | Equity Advisory is going to refine the tool for multiple uses and develop user friendly guidance. | Staff | Annette - A |  | User friendly tool available for coalitions and others who wish to use it. | March: Lukas Soto has agreed to contract with the Alliance to work on this project. A first meeting is scheduled with Lukas, staff, and Equity chairs next quarter. February: The tool will be shared to coalitions with the mini-grant applications.
In Progress | 2023-06-30 | 2023-03-31 | 1.1.5.6 | INITIATIVE: The Alliance will form and support a BIPOC (Black, Indigenous and People of Color) caucus. | Equity Advisory | Annette - A | The Alliance will have a space specifically for BIPOC suicide prevention advocates to meet and work to move things forward.
Achieved | 2023-01-31 | 2023-03-31 |  | Staff will identify leaders for the BIPOC Caucus and provide support as requested. | Staff | Annette - A |  | BIPOC Leaders within the Alliance will be named for this work and an orientation will be given as needed. | March: Members of the BIPOC Caucus were able to identify someone who can provide administrative support for the group. Chairs said they would continue to proivde updates to staff as they come. February: UO Student expressed interest in providing administrative support for the BIPOC Caucus. Staff will follow-up with them to determine next steps.
Not Started | Ongoing | 2023-01-31 |  | Caucus leaders will keep Staff updated on any needs they have and when the group will meet. | Staff | Caucus Leaders - A Annette - S |  | Caucus leaders will tell Staff when meetings are and how Staff can support them.
In Progress | 2023-01-31 | 2023-01-31 | 1.1.5.7 | INITIATIVE: The Alliance will form and support a monthly group to support white allyship and anti-racist education. | Equity Advisory | Annette - A | The Alliance will have a space for White identified suicide prevention advocates to learn how to better integrate liberatory and anti-racist practices into our work.
Achieved | 2023-01-31 | 2023-01-31 |  | Staff will recruit leaders for this group and begin to plan meetings. | Equity Advisory | Annette - A |  | Leaders for this work will be identified. | February: The group will meet again Friday, March 3rd. January: Michelle Bangen and Angela Perry volunteered to co-chair this group. Both have met with Annette multiple times to plan for the group. The first meeting is scheduled for Friday, February 3rd. The group will find a regular day for future meetings.
In Progress | 2023-04-30 | 2023-03-31 |  | Members of the group will each do an individual self-assessment to help identify priority areas for learning and focus. | Equity Advisory | Annette / Lucina - A |  | Members will be able to identify personal priorities for the work which will help to guide the larger group. | March: The group met and discussed part of the self-assessment survey. Due to the length of the survey, it was decided they would continue to review this during the next meeting which will take place next quarter.
In Progress | Ongoing | 2023-02-28 |  | The group will meet on a monthly basis. | Equity Advisory | Annette / Lucina - A |  | White members will continue to do anti-racist work to better the Alliance's ability to advocate for effective and equitable suicide prevention legislation and practices. | February: Due to member availability, the March meeting was cancelled. The group is working to find a new time to meet ongoing.
Achieved | Ongoing | 2023-02-28 | 1.1.6.1 | INITIATIVE: The Alliance staff hosts a quarterly webinar to provide networking support for regional suicide prevention coalitions and other local suicide prevention champions. | Staff & Coalition Leaders Advisory (CLA) | Annette - A | Coalitions across the state are regularly informed about suicide prevention, practice, and policy and have an opportunity to be part of a mutual learning community in which best practices are shared and challenges are addressed. |  | September: Weekly listservs are shared with coalition across the state and staff are in frequent contact with coalition leads. First quarter webinar was attended by 32 people. Focus was on plans for shared messaging for September Suicide Prevention month, an update on a proposed film about suicide (which the group subsequently decided not to sponsor due to concerns re messaging) and an overview of the Summit on the theme "Unpacking Suicidality from a non-pathological, anti-carceral view"
Achieved | Ongoing, Quarterly | 2023-02-28 |  | Staff devlop webinars, recruit participants, and disseminate invitations quarterly. Webinar topics will be based on coalition request and identified needs. | Staff & Coalition Leaders Advisory (CLA) | Annette - A / R Jenn - S |  | Webinars are a useful tool to coalitions and coalitions are connected to one another and the work of the Alliance | March: Webinar discussed Josephine County Coalition, training for ODHS staff on suicide prevention, Coalition grants; 35 attendees; recorded webinar available on Alliance website and YouTube. November: November webinar discussed How do we support survivors of suicide loss; 45 attendees; recorded webinar available on Alliance website and YouTube. June: Quarterly webinar held during June and discussed Washington County messaging efforts, 988 updates, LGBTQ+ mini-grants and resources, and Alliance updates. Live webinar was attended by 33 people from across the state and the recording was uploaded to Alliance's YouTube. Survey was sent to attendees for feedback on overall webinar. This was completed by 4 people. March: Quarterly webinar held during February and discussed lethal means work done by the Alliance. This webinar was recorded and shared to the Alliance website for future access. Live webinar was attended by 26 people from across the state.
Achieved | Ongoing | 2022-09-30 | 1.1.6.2 | INITIATIVE: The Alliance staff hosts a quarterly learning collaborative for regional suicide prevention coalition leaders. | Staff & Coalition Leaders Advisory (CLA) | Annette - A | Build a well-coordinated, informed, and resourced statewide network of suicide prevention coalitions. |  | January: Previously achieved tasks were removed. September: Coalition network leaders meetings held monthly this quarter. Annette also joined some GLS meetings to ensure coordination with GLS grantees. Alliance continues to advocate for mini-grant funding to be distributed to coalitions this fiscal year.
In Progress | Ongoing | 2023-02-28 |  | This quarterly meeting will change to the coalition mini-grant meeting starting August 2023. | Staff & Coalition Leaders Advisory (CLA) | Staff - A / R CLA - C / S |  | Ensure topics are relevant to Coalition needs | September: This learning collaborative is currently occurring monthly. In September, seven counties collaborated on messaging campaign using coffee sleeves that say You Matter and have 988 number and Signs of Hope campaign.
Achieved | Ongoing | 2022-09-30 | 1.1.6.3 | INITIATIVE: Statewide resources, educational opportunities, and programming options are shared to the regional suicide prevention coalition leaders. | Staff | Annette - A | Build a well-coordinated, informed, and resourced statewide network of suicide prevention coalitions. |  | September: Staff receive updates on community opportunities from a variety of partners, stakeholders, and more that are included in listserv emails, and highlighted in webinars and network leader meetings. Working to track contact with engagement with coalitions more closely (see coalition engagement tab).
Achieved | Ongoing | 2022-03-31 |  | Resources, educational opportunities, and programming options are included in weekly / bi-weekly emails to the Alliance listserv which includes coaliton leaders. | Staff | Jenn - R Partners - S |  | Bi-weekly / weekly emails to full Alliance listserv. | These emails go out regularly and also include Alliance related updates.
Early Action | 2023-06-30 | 2023-01-31 | 1.1.6.4 | INITIATIVE: The Alliance staff will administer and evaluate grants for local suicide prevention coalitions. | Staff | Annette - A | Build a well-coordinated, informed, and resourced statewide network of suicide prevention coalitions.
Achieved | Unknown | 2023-02-28 |  | OHA will finalize the contract for AOCMHP and notify when it is signed. | OHA | OHA - A / R |  | The Alliance will have a contract and the funding to complete the work for mini-grants. | January: Staff are in regular contact with OHA staff around the status of the contract.
Achieved | 2023-01-31 | 2023-02-28 |  | Staff will create a timeline for the mini-grant process and review with OHA. | Staff | Staff - A OHA - S |  | Timeline of when applications will be sent out and other tasks for this project will be created as a tool to use. | January: A timeline was drafted and reviewed with OHA. Two meetings have been held with OHA staff to discuss next steps and the process.
Achieved | 2023-02-28 | 2023-02-28 |  | Staff will draft an application with input from the coalitions and UO. | Staff & Coalition Leaders Advisory (CLA) | Annette - A Jenn, UO, Coalitions - S |  | A low barrier application with data collection questions will be drafted with input from coalitions. | February: Staff and OHA determined priority areas/philosophy for mini-grant funding. An application was drafted and reviewed by OHA January: Staff have started this process with coalitions and started to get input.
In Progress | 2023-06-30 | 2023-03-31 |  | Open applications and provide TA as needed. | Staff & Coalition Leaders Advisory (CLA) | Annette - A Jenn, UO, Coalitions - S |  | A low barrier application with data collection questions will be drafted with input from coalitions. | March: Applications and materials were released for coalitions to begin applying for grants. The application is open until June 6th. Two webinars have been provided to review the application and provide time for Q&A around the application process and also project ideas. Webinars are shared on the Alliance website and YouTube. There is also a page on the Alliance webiste with all application materials and Q&A that have come in so far.
Not Started | 2023-08-31 | 2023-03-31 |  | Notify grantees of award amounts. Provide ongoing support through monthly learning collaboratives. | Staff & Coalition Leaders Advisory (CLA) | Annette - A Jenn, UO, Coalitions - S |  | Ongoing TA provided for coalitions. | March: Monthly learning collaboratives will start August and go through June 2023.
Achieved | Ongoing | 2022-09-30 | 1.2.1.1 | INITIATIVE: American Foundation for Suicide Prevention (AFSP) and Suicide Prevention Resource Center (SPRC) national safe messaging projects are promoted on OHA's Suicide Prevention listserv and The Alliance listserv | Staff | Jenn - A | Build a well-coordinated, informed, and resourced statewide network of suicide prevention partners / advocates.
Achieved | Ongoing | 2022-09-30 |  | Resources are shared on the Alliance listserv bi-weekly / weekly | Staff | Jenn - A / R |  | Bi-weekly / weekly emails to full Alliance listserv. | September: These emails go out 2-4 times a month and also include Alliance related updates. We plan to reduce from weekly listserv emails to bi-monthly during the period when we have our communications staff person is out on maternity leave.
Achieved | Ongoing | 2022-09-30 | 1.2.3.4 | INITIATIVE: Alliance to Prevent Suicide Website will continue to make information available regarding Alliance activities, legislative work, opportunities for community members to be involved, and resources. | Staff | Jenn - A | Build a well-coordinated, informed, and resourced statewide network of suicide prevention partners / advocates.
Achieved | Ongoing | 2022-09-30 |  | Staff will update the website at least monthly to make sure information provided is current and up-to-date. | Staff | Jenn - A / R |  | Updated website with current and relevant information. | March: Staff updated the suicide prevention policy pages on the website providing two different ways of reading the information - legislation organized by topic and legislation organized by year passed. September: Staff updated the website on a regular basis with relevant information and to keep it as current as possible. Jenn also developed and recorded and posted a video orienting people to the Alliance projejct planner, meant to be used in conjunction with the OHA orientation to the YSIPP. According to Google analytics (report attached) 1,600 people visited the website. The majority are from the US, but we had a total of 92 visits from other countries, including Canada, Brazil, Germany, China, Phillipines and Bangladesh.
In Progress | 2023-06-30 | 2023-01-31 | 1.2.4.3 | INITIATIVE: The Alliance will schedule presentations with key lawmakers prior to the 2023 long session, participate in planning Capitol Day with the American Foundation for Suicide Prevention, issue a suicide prevention legislative agenda with key partners, and provide testimony as appropriate. | Staff | Annette - A | The Alliance will begin new and build existing relationships with legislators and find key champions for our work moving forward.
Achieved | 2023-01-31 | 2023-01-31 |  | Staff go to the Capitol to leave information on the Alliance's policy agenda and talk with available Senators and their staff. | Staff | Annette - A/R |  | Scan of legislative landscape for the hopeful expansion of legislation. | January: Annette and Jenn went to the Capitol January 25th and talked with multiple staff of Senators and left copies of our policy agenda behind. Two follow-up meetings were scheduled with Senators and we made connections with 6 Senators for follow-up about the legislation the Alliance is leading this session, two of whom signed on as co-sponsors.
Achieved | 2023-02-28 | 2023-01-31 |  | Advertise this years Capitol Days which takes place February 13th and recruit Alliance members to attend. Continue to partner with AFSP Oregon Chapter in planning the event. | Staff | Annette - A/R |  | Scan of legislative landscape for the hopeful expansion of legislation. | January: Staff has shared the event through the listserv multiple times and reached out to key people to attend. Annette advocated for SB 818 (the Alliance's legislation) to be heard during committee that day along with the lifespan legislation which Laura Rose advocated to be read that day.
In Progress | 2023-06-30 | 2023-02-28 |  | Alliance staff, members, and affiliates will provide testimony throughout the 2023 session as needed. | Staff | Annette - A/R |  | Scan of legislative landscape for the hopeful expansion of legislation.
Not Started | 2023-12-31 | 2023-01-31 | 2.1.1.6 | INITIATIVE: The Alliance will make a recommendation to OHA regarding evaluation for suicide prevention workforce training requirements listed in HB 2315 (2021). | Workforce | Annette - A | OHA will take the Alliance's recommendation into consideration when updating evaluation methods for this requirement.
Achieved | 2023-01-31 | 2023-01-31 |  | Alliance will assign a member to review the 3-hour curriculum developed by OHA. | Workforce | Annette - A |  | Workforce Committee representation on the group. | January: Sarah Spafford agreed to do this and will receive OHA stipends through the Alliance for her time.
In Progress | 2023-04-30 | 2023-02-28 |  | Engage Data & Evaluation Committee to make recommendations about how to enhance SB 48 report and any other activities needed to evaluate HB 2315 implementation. | Workforce | Annette - A |  | Meaningful evaluation methods for SB 48 and HB 2315.
In Progress | 2023-12-31 | 2023-03-31 | 2.2.1.1 | INITIATIVE: The Alliance will continue to work towards recommendations in the Lethal Means workplan. | Lethal Means | Jenn - A | The Lethal Means Committee will move forward work they recommended in 2022.
In Progress | 2023-04-30 | 2023-03-31 |  | Make an action plan for how to move this work forward. | Lethal Means | Jenn - A |  | The Committee will have steps to follow to continue their work. | March: Two priority areas were identified and action steps are being created for how they want to accomplish these goals. Key members of the committee were not able to be present at some of the meetings this quarter and the group did not want to make some decisions without them so this is going slower than originally planned. January: The Committee reconvened in January 2023 and reviewed recommendations. They plan to identify the top two recommendations in the February meeting and form two sub-groups that will work those items.
In Progress | 2023-06-30 | 2023-03-31 |  | Partner with Oregon Firearm Safety Coalition (OFSC) on safe storage legislation HB 3513 and provide support as needed. | Lethal Means | Jenn - A |  | Cross group partnership. | March: Staff provided verbal and written testimony discussing the Alliance's support of the bill along with other OFSC members.
In Progress | 2023-12-31 | 2023-01-31 | 2.3.3.4 | INITIATIVE: The Alliance will use the Adi's Act scan and other sources to identify and address structural barriers to implementation for Adi's Act and will make recommendations to OHA and ODE. | Schools | Annette - A | The Alliance will have a list of recommendations for state agencies regarding implementation of Adi's Act. They may also have legislative suggestions for the next long session depending on identified barriers.
Achieved | 2023-01-31 | 2023-01-31 |  | Review Adi's Act Scan from Lines for Life SSPW Team in Committee. | Schools | Annette - A Claire - R |  | Results from scan shared with committee. Next steps to be discussed. | January: Scan was reviewed in committee and members discussed next steps and how they can use the information.
Not Started | 2023-04-30 | 2023-01-31 |  | Schools Committee develop process and timeline for sending feedback to state agencies on Adi's Act Implementation. | Schools | Annette - A Claire / Justin - R |  | Timeline created.
Not Started | 2023-12-31 | 2023-03-31 | 3.1.1.2 | INITIATIVE: The Alliance will pursue involvement and seek representation on the Oregon Health Policy Board's Behavioral Health Committee and monitor OHA's efforts to implement recommendations of the HB 3090 report. | Transitions of Care | Jenn - A | Transitions of Care will have a consistent monitoring schedule of recommendations put forward in the HB 3090 report.
In Progress | 2023-07-31 | 2023-03-31 |  | The Committee will identify when they want reports from OHA about recommendations we are monitoring per the workplan submitted in 2022. A letter will be drafted and Staff will submit this to OHA. | Transitions of Care | Jenn - A TOC Committee - S |  | OHA will have a letter of requests from the Committee on when they would like updates on identified recommendations. | March: Committee members mapped out when they want to hear information and updates about the report this quarter and received feedback from OHA staff on suggested timelines. A letter is being drafted to be sent to OHA to request this. The deadline was extended to account for the legislative session.
In Progress | 2023-04-30 | 2023-03-31 |  | Staff will identify the person to reach out to for involvement on the Oregon Health Policy Board's BH Committee. | Transitions of Care | Jenn - A |  | Staff will know who to connect with about membership on the committee. | March: Jenn and Liz attended the OHPB BH Committee. However, it seemed to be more of an internal structure meeting and not a typical one. So they want to attend another meeting in the future to get a sense of what meetings are like and how we can best engage in the work.
Achieved | 2022-12-31 | 2023-01-31 | 3.3.1.9 | INITIATIVE: The Alliance will introduce a legislative concept to require OHA to identify or develop suicide prevention training for a wide array of medical providers. | Workforce | Annette - A | The Alliance will take the lead on legislation that requests OHA create a training for physical healthcare providers on suicide prevention.
Achieved | 2022-12-31 | 2022-01-31 |  | Find a champion for this work. Reach out to Reynolds, Gelser Blouin, and others. | Workforce | Annette - A |  | The Alliance will find a sponsor for our legislation. | January: Gelser Blouin agreed to sponsor this legislation.
Achieved | 2022-12-31 | 2022-01-31 |  | Finalize legislative concept and submit to Gelser Blouin's office. | Workforce | Annette - A Workforce - S |  | Legislative concept will be submitted for consideration by the Senator. | January: LC was submitted and sent to the office that changes LCs into Bills.
Achieved | 2022-12-31 | 2022-01-31 |  | Find co-sponsors for the legislation. | Workforce | Annette - A Workforce - S |  | Legislative concept will have co-sponsors. | January: Staff found two chief sponsors for the legislation - Senators Gorsek and Gelser Blouin. Two additional legislators signed on as co-sponsors - Senators Taylor and Thatcher. The legislative concept was assigned SB 818 as it's bill number.
In Progress | 2022-12-31 | 2023-03-31 | 3.3.1.10 | INITIATIVE: The Oregon Alliance to Prevent Suicide will advocate for increased access and usage of suicide prevention training by medical professionals. | Workforce | Annette - A | The Alliance will learn what barriers are keeping professionals from completing suicide prevention related trainings and how they can better support them in this work.
In Progress | 2023-06-30 | 2023-03-31 |  | Alliance will work with legislators throughout the long session to get SB 818 passed. | Workforce | Annette - A |  |  | March: SB 818 has moved out of the Senate and is on it's way to the House. Staff and Alliance members have testified in support of the legislation and answered questions regarding mandates.
Not Started | 2023-12-31 | 2023-01-31 |  | A presentation on Zero Suicide with panelists from one or more systems implementing this will occur during the June or December quarterly meeting. | Workforce | Annette - A
Achieved | 2022-12-31 | 2023-01-31 | 4.3.1 | INITIATIVE: The Alliance will issue a suicide prevention legislative agenda for the 2023 session with key priorities named. | Executive | Annette - A | A legislative agenda will be created to help the Alliance focus t heir efforts during the session and let partners know what we are working on.
Achieved | 2022-12-31 | 2023-01-31 |  | The Alliance will vote on key priorities for the 2023 session. Staff will connect with partners on their priorities to see where we can collaborate. | Executive | Annette - A |  | A policy agenda will be created by Alliance members and shared with partners. | January: Alliance membership reviewed and voted on a policy agenda / priorities in 2022. Staff connected with partners on their priority areas and added some to our agenda that we can help collaborate on.
Achieved | 2023-01-31 | 2023-01-31 |  | Staff will draft a legislative agenda one-pager to share with partners, legislators, the Alliance, and on our website. | Executive | Annette - A |  | A one-pager will be finalized to be shared with the public. | January: Staff drafted the one-pager and sent it to a graphic designer to finalize it. The one-pager (pre graphic designer) was shared with Senators during Staff's visit to the Capitol January 25th.
Achieved | 2023-06-30 | 2023-01-31 |  | Staff will monitor bills as they drop to see what falls under suicide prevention and add them to the bill tracker we are using. Staff will track identified bills through our bill tracker which will also be shared with the Alliance. | Executive | Annette - A Jenn - S |  | A shareable bill tracker will be used during the legislative session. | January: A bill tracker was created and some legislation has been added. Staff searched OLIS for bills that have the keyword "suicide" and "schools."
Note on E36: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: should we add in a more formal evaluation for this moving forward?

## Achieved Initiatives
STATUS | YSIPP Year | YSIPP Initiative Number | INITIATIVE / TASK | COMMITTEE / ADVISORY | RASCI-AD | INITIATIVE DESIRED OUTCOME
Achieved | 2021-2022 | 2.2.1.1 | INITIATIVE: The Alliance will create a workplan for Lethal Means work that includes safe storage, collaboration between stakeholders, and policy recommendations. | Lethal Means | Jenn - A | Lethal Means workplan on statewide approach to safe storage, collaboration between stakeholders, and long-term policy recommendations
Achieved | 2021-2022 | 4.3.1 | INITIATIVE: The Alliance will name policy recommendations for 2023 legislative session. | Executive | Annette - A | Alliance voice will be considered when OHA is creating their policy option package to be submitted to the Legislature for the 2023 Legislative Session.
Achieved | 2021-2022 | 1.1.6.1 | INITIATIVE: The Alliance staff hosts a quarterly webinar to provide networking support for regional suicide prevention coalitions and other local suicide prevention champions. | Staff & Coalition Leaders Advisory (CLA) | Annette - A | Coalitions across the state are regularly informed about suicide prevention, practice, and policy and have an opportunity to be part of a mutual learning community in which best practices are shared and challenges are addressed.
Achieved | 2021-2022 | 1.1.6.2 | INITIATIVE: The Alliance staff hosts a quarterly learning collaborative for regional suicide prevention coalition leaders. | Staff & Coalition Leaders Advisory (CLA) | Annette - A | Build a well-coordinated, informed, and resourced statewide network of suicide prevention coalitions.
Achieved | 2021-2022 | 1.1.6.3 | INITIATIVE: Statewide resources, educational opportunities, and programming options are shared to the regional suicide prevention coalition leaders. | Staff | Annette - A | Build a well-coordinated, informed, and resourced statewide network of suicide prevention coalitions.
Achieved | 2021-2022 | 1.2.1.1 | INITIATIVE: American Foundation for Suicide Prevention (AFSP) and Suicide Prevention Resource Center (SPRC) national safe messaging projects are promoted on OHA's Suicide Prevention listserv and The Alliance listserv | Staff | Jenn - A | Build a well-coordinated, informed, and resourced statewide network of suicide prevention partners / advocates.
Achieved | 2021-2022 | 1.2.3.4 | INITIATIVE: Alliance to Prevent Suicide Website will continue to make information available regarding Alliance activities, legislative work, opportunities for community members to be involved, and resources. | Staff | Jenn - A | Build a well-coordinated, informed, and resourced statewide network of suicide prevention partners / advocates.
Achieved | 2021-2023 | 3.1.1.2 | INITIATIVE: The Alliance will respond to OHA's HB 3090 Resurvey Project report (due Fall 2021) and develop a work plan to monitor next steps. | Transitions of Care | Jenn - A | Committee workplan for ongoing monitoring of HB 3090 to ensure correct implementation of legislation

## Stopped or Adjusted Initiatives
STATUS | YSIPP Year | YSIPP Initiative Number | INITIATIVE / TASK | COMMITTEE / ADVISORY | RASCI-AD | INITIATIVE DESIRED OUTCOME
Adjusted | 2021-2022 | 2.3.3.7 | INITIATIVE: Build capacity to monitor implementation of plans for Adi's Act, increase meaningful participation in Adi's Act from school districts, and increase the use of best practices in school districts. Begin by organizing infrastructure and clarifying roles and responsibilities. | Schools | Annette - A | Project plan for Schools Committee to track implementation
Adjusted | 2021-2023 | 4.5.1 | INITIATIVE: The Alliance will continue focus on equity work and will continue to make recommendations to OHA. | Staff | Annette - A | The Alliance will start to engage in using the lens of anti-racist work and liberatory practices in its work and recommendations to OHA and other community partners.
Adjusted | 2021-2024 | 2.1.1.3 | INITIATIVE: HB 2315 Rulemaking process will include recommendations from OHA defining continuing education opportunities that are applicable and relevant to meet the suicide prevention training requirement for relicensure. | Workforce | Annette - A | HB 2315 rules are informed by the Alliance and align with best practice in suicide assessment, treatment, and management.
Adjusted | 2021-2025 | 1.1.4.3 | INITIATIVE: The Alliance will maintain youth reps on each committee and ensure the following populations are represented whenever larger feedback is gathered: member(s) 18 or younger, rural youth, racial/ethnically diverse youth, LGBTQ+ youth. | Staff | Annette - A | Increase meaningful youth and young adult engagement as evidenced by increased participation in committees and / or think tanks
Adjusted | 2021-2026 | 1.1.3.2 | INITIATIVE: OHA and The Alliance continue to build connections with youth-serving community based organizations to invite participation in the Alliance and youth suicide prevention trainings and work. | Staff | Annette - A | Ongoing meaningful youth voice and engagement in Alliance work.
Adjusted | 2021-2027 | 1.2.4.3 | INITIATIVE: The Alliance will schedule presentations with key lawmakers prior to each legislative session. | Staff | Annette - A | Connections with legislators to build relationships and find champions for our work.

## Alliance Contract Deliverables
Alliance Contract Deliverables | ALL ALLIANCE COMMITTEES
PROJECTS
STATUS | PRIORITY | DEADLINE | DATE LAST UPDATED | DELIVERABLE / TASK |  | COMMITTEE / ADVISORY | RASCI-AD | DESIRED OUTOME OF INITIATIVE | TASK DELIVERABLE | NOTES / PROGRESS
Early Action |  | 2023-06-30 | 2022-12-31 | Annual Alliance Survey to assess engagement, satisfaction, and areas for improvement |  | Data & Evaluation & Executive | Staff - A Executive - R Data & Eval / UO Lab - C OHA - I | The Alliance will have a current measurement for progress made and work that still needs to be done to improve how the Alliance interacts with it's members. |  | December: Meeting scheduled with Alliance leadership and OHA to discuss survey and confirm timeline in February 2023. September: Survey completed last year. Will develop tasks and timeline next quarter.
Achieved |  | 2023-02-28 | 2023-03-31 | Identify areas for assessment and survey approach |  | Staff & Alliance Leadership | Annette - A Jenn - S Data & Eval / UO Lab - C OHA - I |  | The Alliance will have a survey approach and identified areas they want to survey members and affiliates about. | March: Alliance staff, Chair, and UO representative met to review survey questions. An idea to add two questions about OHA was proposed. Survey will need to be sent to OHA for approval. September: Survey completed fiscal year. Will develop tasks and timeline next quarter.
In Progress |  | 2023-03-31 | 2023-03-31 | Develop survey methodology and questions with input from UO Lab and final approval by OHA per contract |  | Staff & Alliance Leadership | Annette - A Jenn - S Data & Eval / UO Lab - C OHA - I |  | Final survey completed and ready to send to members and affiliates. | March: OHA was not able to be at the March 31st meeting to discuss the survey due to last minute scheduling issues. UO approved methodololgy and questions. Just need to send survey to OHA for their approval. September: Survey completed last fiscal year. Will develop tasks and timeline next quarter.
Not Started |  | 2023-05-31 | 2023-03-31 | Dissimenate survey to Alliance (decide if to full Alliance or just membership) with survey closing May 27, 2022 |  | Staff | Staff - A OHA - S |  | Survey is sent to Alliance listserv. | March: Timeline changed for this as it was decided to have time at the June quarterly for people to complete the survey like last time.
Not Started |  | 2023-06-30 | 2023-03-31 | Results are gathered and put into a report format |  | Staff | Staff - S |  | Results from survey are prepared and ready to be reviewed by staff and appropriate committees. | March: Timeline changed for this as it was decided to have time at the June quarterly for people to complete the survey like last time.
Not Started |  | 2023-06-30 | 2023-03-31 | Review results with Executive & Data & Evaluation |  | Data & Evaluation & Executive | Staff - A |  | Committees will be able to provide feedback based on results for next steps. | March: Timeline changed for this as it was decided to have time at the June quarterly for people to complete the survey like last time.
Not Started |  | 2023-07-31 | 2023-03-31 | Submit report to OHA |  | Staff | Staff - A / R |  | Contract deliverable met. | March: Timeline changed for this as it was decided to have time at the June quarterly for people to complete the survey like last time.
Not Started |  | 2023-06-30 | 2023-03-31 | Create and disseminate satisfaction survey specifically for Alliance Chairs. |  | Staff | Staff - A / R |  | Alliance staff will have insight into satisfaction rates for current Alliance Chairs and areas of improvement. | March: Timeline changed for this as it was decided to have time at the June quarterly for people to complete the survey like last time.
Not Started |  | 2023-09-30 | 2023-03-31 | Review survey and results with full Alliance at Quarterly meeting |  | Staff | Staff - A |  | Full Alliance will see the results and provide feedback. | March: Timeline changed for this as it was decided to have time at the June quarterly for people to complete the survey like last time.
In Progress |  | 2023-06-30 | 2023-03-31 | Expand and Maintain Alliance Membership |  | Staff & Executive | Annette - A Exec - R Jenn - S | Membership will meet both SB 707 requirements and will reflect Oregonians. |  | September: Provided Alliance orientation in one-on-ones with 7 individuals.
Achieved |  | 2022-12-31 | 2023-03-31 | Decide timeline / process for Alliance Membership applications. |  | Staff & Executive | Annette - A Jenn - S Exec - C/I |  | Alliance leadership will have an identified process for when applications are accepted and voted on. | March: Timeline was approved by Executive - Applications open from March-April, Executive discusses and votes May, names sent to OHA May, receive letters from OHA June or September December: Process proposed. Will discuss and vote during Executive Committee meeting January 2023. August: Executive talked about keeping membership applications open for specific SB 707 categories and haing a general application time during the beginning of a new calendar year. Staff will suggest a specific timeline for Executive to review, discuss, approve.
Achieved |  | 2023-03-01 | 2022-08-30 | Send email to Alliance Listserv asking for membership recommendations |  | Staff | Annette - A Jenn - R |  | Existing members and affiliates can recommend people they know to be considered for Alliance membership. Existing affiliates can apply to become full-members. | March: Recruitment emails have gone out both through the Alliance listserve and targeted recruitment by Executive Committee members and other Alliance members.
Not Started |  | 2023-05-31 | 2022-08-30 | Executive votes on recommended members during May Executive meeting |  | Staff & Executive | Annette - A Executive R Jenn - S |  | A list of proposed members will be ready to move forward to the full Alliance.
Not Started |  | 2023-05-31 | 2022-08-30 | Staff Send names of new members to OHA for appointment |  | Staff | Annette - A / R Jenn - S |  | Once appointed, the Alliance will have new members.
Not Started |  | Unknown 2023 | 2022-09-30 | Alliance Funding Priorities Submitted to OHA |  | Executive | Annette - A | Alliance voice will be considered when OHA is creating their policy option package to be submitted to the Legislature for the 2023 Legislative Session. |  | September: Funding and policy priorities submitted last fiscal year. In August, we were informed that the coalition mini-grant funds, previously approved to be managed by the Alliance through AOCMHP starting July 1st, would be retained and administered by OHA due to categorical designation of funds by the OHA contract office. Executive Committee requested letter of concern to be sent to OHA leadership. Letter to be sent next quarter.
Not Started |  | Unknown 2023 | 2022-08-30 | This contract deliverable was completed through a YSIPP Initiative listed on the "All Alliance YSIPP Initiatives" tab. |  | Executive | Annette - A / R Jenn - S
In Progress |  | 2023-12-31 | 2023-03-31 | Alliance Committees will Select and Vote on new Chairs for the upcoming fiscal year |  | Staff & Committees | Annette - A Committees - R | Committees will have appropriate leadership to help move the work forward. |  | September: New committee chairs, Justin Potts and Claire Kille, approved for Schools Committee. Seeking new co-chairs for Transition of Care and Evaluation and Data Committees. Charlette Lumby voted in as new co-chair of the Alliance and Galli Murray renewed for second term as chair.
In Progress |  | 2023-11-30 | 2023-03-31 | After members are appointed by OHA, Committees will propose Committee Chairs for the upcoming Fiscal Year |  | Annette & Committees | Annette - A Committees - R Jenn - S |  | Specific individuals to be considered for committee leadership. | March: Deadline changed to match with approved timeline by Executive for new members and to allow OHA time to approve new members and send out letters. Liz Schwarz was voted in as a new co-chair for Transitions of Care Committee. September: New committee chairs, Justin Potts and Claire Kille, approved for Schools Committee. Seeking new co-chairs for Transition of Care and Evaluation and Data Committees. Charlette Lumby voted in as new co-chair of the Alliance and Galli Murray renewed for second term as chair.
In Progress |  | 2023-12-31 | 2023-03-31 | Committee members will vote on recommended committee chairs |  | Annette & Committees | Annette - A Committees - R Jenn - S |  | Committees will select their chairs for the upcoming fiscal year.
Not Started |  | 2024-01-31 | 2023-03-31 | Committee chairs will be appointed and, if they are a new chair, oriented to their roles. |  | Annette & Committees | Annette - A Committees - R Jenn - S |  | Chairs will be appointed. | March: Jenn oriented new TOC Co-Chair Liz Schwarz. September: Annette oriented new Alliance chair, Charlette Lumby, and Schools co-chairs.
Achieved |  | 2022-12-31 | 2022-09-30 | YSIPP Project Planning |  | Staff | Annette - A Jenn - S | Alliance staff will have a clear process to show progress on Alliance work to both members and community stakeholders. |  | September: Each committee began reviewing assigned initiatives from previous year, to discuss whether initiative should stop, start or be revised. Recommendations to be submitted at November exec.
Achieved |  | 2022-09-30 | 2022-08-30 | Assess relevant YSIPP Priorities for current fiscal year |  | Staff | Annette - A Jenn - S |  | Priority initiatives identified.
Achieved |  | 2022-11-30 | 2022-08-30 | Meet with Committee chairs to review assigned YSIPP Initiatives and begin project planning process |  | Staff & Committees | Annette - A OHA - S |  | Chairs to provide input on their work. | August: OHA Staff reviewed process for selecting new initiatives during Executive Committee meeting and will review this during September Quarterly. September: See "All Alliance YSIPP Initiatives" Tab lines 4-8 for details on this specific action item. Deadline extended to match deadline given on the other tab.
Achieved |  | 2022-09-30 | 2022-09-30 | Upload OHA video on navigating SP Framework to website |  | OHA and Staff | Jenn - A OHA - R Annette - S |  | Website uploaded to website | August: OHA Staff have video complete. Alliance Staff need to follow-up with them on status and uploading to website. September: Video uploaded to Alliance website on the YSIPP 21-25 page.
Achieved |  | 2022-06-30 | 2022-08-30 | Jenn will create video providing an overview of the Project Plan highlighting specific initiatives and tasks. |  | Staff | Jenn - A / R |  | Educational video for Alliance leadership and members around how to navigate this project plan to stay updated with initiative / task process | March: See above. June: Alliance staff drafted outline for video and will record it for initial review. August: OHA reviewed video and sent feedback. Staff needs to follow-up on next steps. September: Video uploaded to Alliance webiste on the priority initiatives pages.
In Progress |  | Ongoing | 2023-03-31 | Equity Work |  | Equity Advisory | Annette - A | The Alliance will start to engage in use the lens of anti-racist work and liberatory practices in it's work and recommendations to OHA and other community partners. |  | September: See lines 32 - 37 of the YSIPP initiatives for details.Equity Advisory group met monthly this quarter.
In Progress |  | Ongoing | 2022-03-31 | This contract deliverable is documented through YSIPP Initiatives listed on the "All Alliance YSIPP Initiatives" tab. |  | Equity Advisory | Annette - A Jenn - S UPRISE - C
In Progress |  | Ongoing | 2023-03-31 | Youth and Young Adult Engagement |  | Staff | Annette - A Jenn - R YET - S | Increase meaningful youth and young adult engagement as evidenced by increased participation in committees and / or think tanks. Youth and young adult represented and their voices heard on the Alliance. |  | September: Individual meetings for support and planning with youth members Sicche, Aaron and Jesus.
In Progress |  | Ongoing | 2022-03-31 | This contract deliverable is documented through YSIPP Initiatives listed on the "All Alliance YSIPP Initiatives" tab. |  | Staff | Annette - A Jenn - R YET - S

## Parking Lot (hidden)
Data & Ealuation
OHA create a form for local YSIPP intitiatives / interface

## Staff Template (hidden)
TEMPLATE
|  |  | PROJECTS |  |  | DELIVERABLE(S)
STATUS | PRIORITY | DEADLINE | TASK | DESCRIPTION | ASSIGNED TO | NEXT STEPS & MILESTONES

## KEY
STATUS KEY | Definitions
Not Started | Nothing for initiative / action step has started Some or all tasks are overdue
Planning | In planning stage Some or all tasks are overdue
Early Action | one or two steps have been taken Some or all tasks are overdue
In Progress | significant progress has been made Some or all tasks are overdue
Not Started | Nothing for initiative / action step has started Meeting most, but not all deadlines
Planning | In planning stage Meeting most, but not all deadlines
Early Action | one or two steps have been taken Meeting most, but not all deadlines
In Progress | significant progress has been made Meeting most, but not all deadlines
Not Started | Nothing for initiative / action step has started On track with agreed upon deadlines
Planning | In planning stage On track with agreed upon deadlines
Early Action | one or two steps have been taken On track with agreed upon deadlines
In Progress | significant progress has been made On track with agreed upon deadlines
Achieved | fully achieved and sustainable On track with agreed upon deadlines
Priority Changed | Committee, Alliance, and / or staff agreed that this specific action step / initiative is no longer a priority for the Committee, Alliance, and / or staff
Needs Follow-Up | Staff need to follow-up with committee / advisory group / OHA on the task to ensure it's still a priority or if it needs to be adjusted